## About this template
ISO 27001 implementation plan (ISO/IEC 27001:2022)
Sovereign Secure Ltd ¦ Version: October 2026 ¦ Free to use and adapt within your organisation
What this is
A project plan for implementing ISO/IEC 27001:2022, including Amendment 1 (2024). It turns the 11-step roadmap on our ISO 27001 implementation page into 31 tasks in six phases, each with the clauses it meets, the output it produces and an indicative month from a six-month plan for a mid-sized organisation. Add owners, start dates and durations, and the Summary sheet shows progress by phase.
Read the guide | https://sovereignsecure.co.uk/iso-27001-implementation/
What is in this workbook
Summary | Progress by phase and overall, the six milestones and the planned end date of each phase. It updates as you fill in the project plan.
Project plan | 31 tasks across the 11 steps and six phases: plan, assess risk, build, operate, check and certify.
Roles | Who does what in an ISO 27001 implementation, with a column to name each person.
How to use it
Step 1 | Name the ISMS owner and the people in each role on the Roles sheet first.
Step 2 | On the Project plan sheet, give each task an owner, a start date and a duration in weeks. The end date calculates itself.
Step 3 | Use the Indicative month column as a starting point only. Small, cloud-based teams are often faster; larger or multi-site scopes take longer.
Step 4 | Switch on controls that produce periodic records, such as access reviews and backup tests, as early as you can, so there are records to sample before the audits.
Step 5 | Update the Status column each week. The Summary sheet shows progress by phase and which milestones are done.
Step 6 | Leave time between the internal audit, the management review and Stage 1 to fix what they find.
Important
Timings are indicative. For most small and mid-sized organisations, ISO 27001 takes three to nine months from start to certificate; scope, starting maturity and how quickly decisions are made matter more than headcount alone.
ISO 27001 sets no minimum period for running the ISMS before certification, but the certification body needs records to sample and a completed internal audit and management review.
This plan does not reproduce ISO/IEC 27001, and clause numbers are references only. Following it does not on its own make an organisation conform to ISO 27001 or guarantee certification, which only an independent certification body can grant.
Free to use and adapt within your organisation.
Get help
Enquiry form | Use the enquiry form on our ISO 27001 implementation page, which is already set to ISO 27001
Phone | +44 161 523 5276
Email | contactus@sovereignsecure.co.uk
Website | sovereignsecure.co.uk
About Sovereign Secure | Sovereign Secure Ltd is an ISO 27001-certified UK consultancy, a PCI SSC-approved QSA company and an IASME-licensed Cyber Essentials certification body. We can validate your self-assessment with an ISO 27001 gap analysis, run your internal audit or support the whole project. Certification audits are carried out by an independent certification body, our partner MQA International. Companies House 08334453. 16 Whalley Road, Accrington, Lancashire, BB5 1AA.

## Summary
ISO 27001 implementation plan: summary
Sovereign Secure Ltd ¦ sovereignsecure.co.uk ¦ +44 161 523 5276 ¦ Version: October 2026
Progress by phase
Phase | Tasks | Done | In progress | Not started | Done (%) | Planned end
1. Plan | 8 | 0 | 0 | 8 | 0%
2. Assess risk | 5 | 0 | 0 | 5 | 0%
3. Build | 7 | 0 | 0 | 7 | 0%
4. Operate | 3 | 0 | 0 | 3 | 0%
5. Check | 4 | 0 | 0 | 4 | 0%
6. Certify | 4 | 0 | 0 | 4 | 0%
All phases | 31 | 0 | 0 | 31 | 0%
Milestones
Milestone | Phase | Status
Scope and plan approved by top management | 1. Plan | Not started
Risk owners approve treatment and accept residual risk | 2. Assess risk | Not started
Every applicable control has an owner and is running | 3. Build | Not started
Enough records for an auditor to sample | 4. Operate | Not started
No open major findings | 5. Check | Not started
Certificate issued; surveillance audits planned for years two and three | 6. Certify | Not started
Do not type in this sheet: every figure is a formula. A milestone shows Done when every task in its phase is done. Planned end is the latest end date entered for that phase.

## Project plan
ISO 27001 implementation plan
Sovereign Secure Ltd ¦ sovereignsecure.co.uk ¦ +44 161 523 5276 ¦ Version: October 2026 ¦ 11 steps in six phases, ISO/IEC 27001:2022
Fill in the red columns: owner, start date, duration in weeks and status. The end date calculates itself. Rows marked (milestone) close a phase. Insert new tasks above the last row so the Summary counts them.
ID | Phase | Step | Task | Clauses | Output | Indicative month | Owner | Start date | Duration (weeks) | End date | Status | Notes
T01 | 1. Plan | 1. Secure commitment and set up the project | Agree why you want certification: a customer, a tender or risk reduction | 5.1 | Agreed reason and target | Month 1
T02 | 1. Plan | 1. Secure commitment and set up the project | Name a sponsor in top management and an ISMS owner | 5.1, 5.3 | Sponsor and ISMS owner named | Month 1
T03 | 1. Plan | 1. Secure commitment and set up the project | Set a budget and pick a target audit date | 7.1 | Approved budget and plan | Month 1
T04 | 1. Plan | 2. Understand context and set the scope | Record internal and external issues, including whether climate change is relevant | 4.1 | Issues register | Month 1
T05 | 1. Plan | 2. Understand context and set the scope | List interested parties and their requirements, and decide which the ISMS will address | 4.2 | Interested parties register | Month 1
T06 | 1. Plan | 2. Understand context and set the scope | Set the scope: services, sites, teams and systems, and where they connect to activities outside it | 4.3, 4.4 | ISMS scope statement | Month 1
T07 | 1. Plan | 3. Run a gap analysis | Compare current practice with every clause and Annex A control | Not required by the standard | Gap register | Month 1
T08 | 1. Plan | 3. Run a gap analysis | Rank the gaps and get the scope and plan approved by top management | Not required by the standard | Approved roadmap (milestone) | Month 1
T09 | 2. Assess risk | 4. Assess risks | Define the risk method, risk acceptance criteria and risk owners | 6.1.2 | Risk methodology | Month 2
T10 | 2. Assess risk | 4. Assess risks | Identify, analyse and evaluate risks to the confidentiality, integrity and availability of information in scope | 6.1.2, 8.2 | Risk register | Month 2
T11 | 2. Assess risk | 5. Plan risk treatment and write the SoA | Choose how to treat each risk and decide the controls you need | 6.1.3 | Risk treatment plan | Month 2
T12 | 2. Assess risk | 5. Plan risk treatment and write the SoA | Compare your controls with the 93 Annex A controls and record every decision | 6.1.3 d) | Statement of Applicability | Month 2
T13 | 2. Assess risk | 5. Plan risk treatment and write the SoA | Risk owners approve the treatment plan and accept the residual risk | 6.1.3, 8.3 | Approval record (milestone) | Month 2
T14 | 3. Build | 6. Write policies and set objectives | Write and approve the information security policy | 5.2 | Approved policy | Months 2 to 4
T15 | 3. Build | 6. Write policies and set objectives | Write the topic-specific policies your SoA needs, for how you actually work | Annex A 5.1 | Approved topic-specific policies | Months 2 to 4
T16 | 3. Build | 6. Write policies and set objectives | Set measurable security objectives with owners and dates | 6.2 | Objectives register | Months 2 to 4
T17 | 3. Build | 6. Write policies and set objectives | Put document control in place | 7.5 | Document register | Months 2 to 4
T18 | 3. Build | 7. Implement controls and train people | Put the selected controls in place: technical changes, new processes, supplier terms | 8.1, Annex A | Controls in place | Months 2 to 4
T19 | 3. Build | 7. Implement controls and train people | Define and record competence for people whose work affects security | 7.2 | Competence records | Months 2 to 4
T20 | 3. Build | 7. Implement controls and train people | Run awareness training and record who completed it | 7.3, 7.4 | Training records (milestone) | Months 2 to 4
T21 | 4. Operate | 8. Operate, monitor and measure | Switch on controls with periodic records early, such as access reviews and backup tests | 8.1 | First records | Months 3 to 5
T22 | 4. Operate | 8. Operate, monitor and measure | Run the ISMS and keep the records auditors sample: access reviews, incidents, supplier checks, backup tests, changes | 8.1, 8.2, 8.3 | Records | Months 3 to 5
T23 | 4. Operate | 8. Operate, monitor and measure | Decide what to measure and analyse the results | 9.1 | Metrics and analysis (milestone) | Months 3 to 5
T24 | 5. Check | 9. Carry out an internal audit | Set the audit programme and choose an auditor who is objective and impartial | 9.2 | Audit programme | Month 5
T25 | 5. Check | 9. Carry out an internal audit | Audit the whole ISMS and report the findings | 9.2 | Internal audit report | Month 5
T26 | 5. Check | 10. Hold a management review and fix findings | Hold the management review with every input clause 9.3 lists, and record decisions | 9.3 | Management review minutes | Month 5
T27 | 5. Check | 10. Hold a management review and fix findings | Correct each nonconformity and remove its root cause | 10.1, 10.2 | Corrective action log (milestone) | Month 5
T28 | 6. Certify | 11. Certification audit | Book Stage 1 and Stage 2 with the certification body | Certification body | Audit dates | Month 6 onwards
T29 | 6. Certify | 11. Certification audit | Stage 1: documentation and readiness review | Certification body | Stage 1 report | Month 6 onwards
T30 | 6. Certify | 11. Certification audit | Resolve Stage 1 concerns, then Stage 2: effectiveness audit | Certification body | Stage 2 report | Month 6 onwards
T31 | 6. Certify | 11. Certification audit | Close any major nonconformities and agree corrective action plans for minor ones | 10.2 | Certificate issued (milestone) | Month 6 onwards

## Roles
Who does what in an ISO 27001 implementation
Sovereign Secure Ltd ¦ sovereignsecure.co.uk ¦ +44 161 523 5276 ¦ Version: October 2026
ISO 27001 is a management system, so the work spreads well beyond IT. Name a person or team for each role; the internal auditor must be independent of the work they audit.
Role | Responsibility | Name or team | Notes
Top management | Sets direction, provides resources, approves policy, leads management review
ISMS owner | Runs the project and then the ISMS day to day
Risk owners | Approve risk treatment and accept residual risk
Control owners (IT, HR, facilities, development) | Operate controls and keep the records
All staff | Follow policy, complete training, report security events
Internal auditor | Audits objectively and never audits their own work
Consultant (optional) | Guides, drafts, trains and checks readiness
Certification body | Audits and decides on certification; cannot advise