## About this template
PCI DSS compliance roadmap
Free template from Sovereign Secure Ltd, a PCI SSC-approved Qualified Security Assessor (QSA) company
About this template
What it is | A working plan for PCI DSS compliance in five phases: scoping, gap analysis, remediation, assessment and maintenance. It holds 49 tasks taken from our PCI DSS compliance roadmap guide, each with the requirement it supports, the output an assessor will ask to see and a typical owner.
Version | October 2026, based on PCI DSS v4.0.1. The requirements that v4.0 future-dated became mandatory on 31 March 2025, so they are included as baseline tasks.
Who it is for | Merchants and service providers planning a first Report on Compliance (ROC) or Self-Assessment Questionnaire (SAQ), or tidying up a programme before their next assessment. A merchant on a short SAQ will mark many rows "Not applicable".
Licence | Free to use and adapt within your organisation.
Guide | sovereignsecure.co.uk: PCI DSS compliance roadmap
How to use it
1. Scope first | Work through phase 1 before anything else. Every later cost depends on the size of your cardholder data environment.
2. Name owners | Replace "Typical owner" with a named person in "Owner (name)". Every task needs one owner, even when several teams help.
3. Set dates | Enter a start date and a deadline for each task. Leave contingency before the assessment date: late scans or a missing provider AOC can delay sign-off by weeks.
4. Track status | Choose a status from the dropdown. A deadline turns red once it has passed and the task is not Done or Not applicable.
5. Keep the evidence | Use "Output or evidence" as your checklist for the evidence library, labelled by requirement.
6. Add your own rows | Insert new rows inside the table so the dropdowns and date formats carry over.
Progress by phase
Phase | Tasks | Done | Overdue
1. Scoping | 8 | 0 | 0
2. Gap analysis | 5 | 0 | 0
3. Remediation | 16 | 0 | 0
4. Assessment | 9 | 0 | 0
5. Maintenance | 11 | 0 | 0
All phases | 49 | 0 | 0
Important
Not the standard | Requirement numbers are given for reference only. The official PCI DSS v4.0.1 text, with its testing procedures, is free from the PCI SSC document library.
Official text | www.pcisecuritystandards.org/document_library/
Your assessor decides | This roadmap is general guidance. Your acquirer decides your validation route, and your QSA, or your acquirer if you complete an SAQ, decides what evidence your assessment needs.
No card data | Never put card data in this workbook or in your evidence. Mask PANs in screenshots and exports.
Get help
Contact us | sovereignsecure.co.uk/contact-us/
Phone | +44 161 523 5276
Email | contactus@sovereignsecure.co.uk
How we can help | Sovereign Secure Ltd is a PCI SSC-approved QSA company. Our PCI DSS consultancy team can build and run the roadmap with you, and our QSAs can carry out the formal assessment when you are ready, within PCI SSC independence rules.
Sovereign Secure Ltd (Sovereign Secure Limited), company number 08334453. 16 Whalley Road, Accrington, Lancashire, BB5 1AA. sovereignsecure.co.uk
Formulas:
Overdue = COUNTIFS('Roadmap'!$B5:B300,[Phase],'Roadmap'!$I5:I300,"<"&TODAY(),'Roadmap'!$J5:J300,"<>Done",'Roadmap'!$J5:J300,"<>Not applicable")

## Roadmap
PCI DSS compliance roadmap: five phases, tasks, owners and deadlines
Free template from Sovereign Secure Ltd ¦ sovereignsecure.co.uk ¦ +44 161 523 5276 ¦ Version October 2026 ¦ PCI DSS v4.0.1
Each task from our PCI DSS compliance roadmap guide, in order, with the PCI DSS v4.0.1 requirement it supports and the output your assessor will expect. Add a named owner, start date and deadline for each row. A deadline turns red once it has passed and the task is not Done. Mark tasks outside your scope "Not applicable" rather than deleting them.
ID | Phase | Task | PCI DSS ref. | Output or evidence | Typical owner | Owner (name) | Start | Deadline | Status | Notes
P1-01 | 1. Scoping | List every payment channel: website, payment pages, phone, call recordings, email, terminals, mail | 12.5.2 | Payment channel list | Programme lead |  |  |  | Not started
P1-02 | 1. Scoping | Draw the current network diagram | 1.2.3 | Network diagram | IT or security lead |  |  |  | Not started
P1-03 | 1. Scoping | Draw data flow diagrams for every card data flow | 1.2.4 | Data flow diagrams | IT or security lead |  |  |  | Not started
P1-04 | 1. Scoping | Inventory the in-scope system components, including connected-to systems | 12.5.1 | System inventory | IT or security lead |  |  |  | Not started
P1-05 | 1. Scoping | List third-party service providers and what each does for you | 12.8.1 | Service provider list | Procurement or programme lead |  |  |  | Not started
P1-06 | 1. Scoping | Search for stray card data in file shares, email, logs, tickets and backups | 3.2.1, 12.5.2 | Card data discovery results | IT or security lead |  |  |  | Not started
P1-07 | 1. Scoping | Decide whether to use segmentation to reduce scope | 12.5.2, 11.4.5 | Scope decision record | IT or security lead |  |  |  | Not started
P1-08 | 1. Scoping | Document and confirm the scope | 12.5.2 | Scope confirmation record | Programme lead |  |  |  | Not started
P2-01 | 2. Gap analysis | Confirm your merchant or service provider level and validation route (SAQ or ROC) with your acquirer | - | Acquirer's confirmation | Finance or payments lead |  |  |  | Not started
P2-02 | 2. Gap analysis | If self-assessing, choose the SAQ whose eligibility criteria you fully meet | - | SAQ eligibility record | Compliance lead |  |  |  | Not started
P2-03 | 2. Gap analysis | Compare current controls with every applicable requirement | All applicable | Gap register | Programme lead, often with a consultant |  |  |  | Not started
P2-04 | 2. Gap analysis | Record the owner, effort and cost of each gap | - | Costed gap register | Programme lead |  |  |  | Not started
P2-05 | 2. Gap analysis | Present the costed plan and timeline to the board for sign-off | - | Approved plan and budget | Executive sponsor |  |  |  | Not started
P3-01 | 3. Remediation | Reduce scope first: tokenisation, validated P2PE or outsourced payment pages | - | Updated scope and diagrams | IT or security lead |  |  |  | Not started
P3-02 | 3. Remediation | Replace or isolate unsupported software | 6.3.3, 12.3.4 | Upgrade records | IT lead |  |  |  | Not started
P3-03 | 3. Remediation | MFA for all non-console access into the CDE | 8.4.2 | MFA configuration evidence | IT lead |  |  |  | Not started
P3-04 | 3. Remediation | Fix weak segmentation between the CDE and other networks | Requirement 1 | Network security control rules and diagrams | Network lead |  |  |  | Not started
P3-05 | 3. Remediation | Remove stored card numbers you do not need, and render the rest unreadable | 3.2.1, 3.5.1 | Retention and encryption evidence | IT lead |  |  |  | Not started
P3-06 | 3. Remediation | Passwords of at least 12 characters (or 8 where a system cannot support 12) | 8.3.6 | Password configuration | IT lead |  |  |  | Not started
P3-07 | 3. Remediation | Authenticated internal vulnerability scanning | 11.3.1.2 | Scanning credentials and scan reports | IT or security lead |  |  |  | Not started
P3-08 | 3. Remediation | Automated mechanisms for audit log review | 10.4.1.1 | Log review tooling and records | IT or security lead |  |  |  | Not started
P3-09 | 3. Remediation | Anti-phishing mechanisms | 5.4.1 | Email security configuration | IT lead |  |  |  | Not started
P3-10 | 3. Remediation | Awareness training that covers phishing and social engineering | 12.6.3.1 | Training content and records | HR or compliance lead |  |  |  | Not started
P3-11 | 3. Remediation | Payment page script inventory, authorisation and integrity (e-commerce) | 6.4.3 | Script inventory with justifications | Web or development lead |  |  |  | Not started
P3-12 | 3. Remediation | Change and tamper detection on payment pages (e-commerce) | 11.6.1 | Detection mechanism and alert records | Web or development lead |  |  |  | Not started
P3-13 | 3. Remediation | Targeted risk analysis for every requirement where you set the frequency | 12.3.1 | Targeted risk analyses | Compliance lead |  |  |  | Not started
P3-14 | 3. Remediation | Policies, procedures and documented roles for each requirement | x.1.1, x.1.2 | Approved policies and role assignments | Compliance lead |  |  |  | Not started
P3-15 | 3. Remediation | Service provider agreements, responsibility matrix and current AOCs | 12.8.2, 12.8.4, 12.8.5 | Responsibility matrix and provider AOCs | Procurement or programme lead |  |  |  | Not started
P3-16 | 3. Remediation | Build the evidence library, labelling each item with its requirement | - | Evidence library | Programme lead |  |  |  | Not started
P4-01 | 4. Assessment | Book your QSA, or set the SAQ submission date with your acquirer | - | Confirmed assessment dates | Programme lead |  |  |  | Not started
P4-02 | 4. Assessment | Quarterly internal vulnerability scans for the period | 11.3.1 | Four quarters of scan reports | IT or security lead |  |  |  | Not started
P4-03 | 4. Assessment | Quarterly external ASV scans by a PCI SSC Approved Scanning Vendor | 11.3.2 | Passing ASV scan reports | IT or security lead |  |  |  | Not started
P4-04 | 4. Assessment | Internal and external penetration tests | 11.4.2, 11.4.3 | Penetration test reports | IT or security lead |  |  |  | Not started
P4-05 | 4. Assessment | Segmentation testing, if you rely on segmentation | 11.4.5, 11.4.6 | Segmentation test report | IT or security lead |  |  |  | Not started
P4-06 | 4. Assessment | Fix and retest or rescan anything found | 11.3, 11.4.4 | Retest and rescan evidence | Control owners |  |  |  | Not started
P4-07 | 4. Assessment | Readiness review a few weeks before fieldwork | - | List of missing evidence | Programme lead |  |  |  | Not started
P4-08 | 4. Assessment | Fieldwork: interviews, system sampling and evidence review (ROC) | - | Answers to the assessor's requests | Programme lead |  |  |  | Not started
P4-09 | 4. Assessment | Receive the ROC and AOC, or sign the SAQ and AOC, and submit to your acquirer | - | ROC or SAQ, and AOC | Executive officer |  |  |  | Not started
P5-01 | 5. Maintenance | Monitor logs and alert on failures of critical security controls (continuous) | 10.7.2 | Alert and response records | IT or security lead |  |  |  | Not started
P5-02 | 5. Maintenance | Quarterly internal and external vulnerability scans | 11.3.1, 11.3.2 | Scan reports each quarter | IT or security lead |  |  |  | Not started
P5-03 | 5. Maintenance | Six-monthly review of network security control rules | 1.2.7 | Rule review records | Network lead |  |  |  | Not started
P5-04 | 5. Maintenance | Six-monthly user access review | 7.2.4 | Access review records | IT lead |  |  |  | Not started
P5-05 | 5. Maintenance | Annual penetration testing, and after significant change | 11.4 | Penetration test reports | IT or security lead |  |  |  | Not started
P5-06 | 5. Maintenance | Annual security awareness training and policy acknowledgement | 12.6.3 | Training and acknowledgement records | HR or compliance lead |  |  |  | Not started
P5-07 | 5. Maintenance | Confirm scope at least every 12 months, and after significant change | 12.5.2 | Scope confirmation record | Programme lead |  |  |  | Not started
P5-08 | 5. Maintenance | Review each targeted risk analysis at least every 12 months | 12.3.1 | Reviewed analyses | Compliance lead |  |  |  | Not started
P5-09 | 5. Maintenance | Test the incident response plan at least every 12 months | 12.10.2 | Exercise record and actions | Security lead |  |  |  | Not started
P5-10 | 5. Maintenance | Check every service provider's PCI DSS status at least every 12 months | 12.8.4 | Current provider AOCs | Procurement or programme lead |  |  |  | Not started
P5-11 | 5. Maintenance | After any significant change: re-scope, rescan, retest and confirm requirements are in place | 6.5.2, 12.5.2 | Change records and test evidence | Change owner |  |  |  | Not started