## About this template
Penetration test preparation checklist
Free template from Sovereign Secure Ltd, a PCI SSC-approved QSA company, IASME-licensed Cyber Essentials certification body and ISO 27001 certified
About this template
What it is | A printable checklist of everything your team needs to prepare for a penetration test, from agreeing objectives and scope to backups, test accounts and the debrief. It mirrors our guide on how to prepare for a penetration test.
Version | October 2026.
Who it is for | IT leads, security managers and anyone organising a penetration test of networks, applications, cloud or people.
Licence | Free to use and adapt within your organisation.
Web page | sovereignsecure.co.uk/preparing-your-team-for-a-pen-test-a-strategic-checklist-for-2026/
How to use it
1. Start early | Most of the preparation takes two to four weeks. Start with the "4 weeks before" rows.
2. Assign people | Add the person responsible and a target date for each task.
3. Track progress | Set Status to Done, In progress, Not started or Not applicable as you go.
4. Share it | Send the completed scoping rows to your testing provider, so the proposal reflects your real scope.
Progress summary
Status | Rows
Done | 0
In progress | 0
Not started | 0
Not applicable | 0
Not yet answered | 24
Rows listed | 24
Important
General guidance | This checklist is general guidance. Your testing provider will confirm the exact preparation your test needs during scoping.
Authorisation | Never allow testing to start without written authorisation from someone entitled to give it for every system in scope.
No real credentials | Do not record passwords, keys or other secrets in this workbook. Share test credentials with your tester through a secure channel.
Get help
Next step | Request a penetration testing quote
Phone | +44 161 523 5276
Email | contactus@sovereignsecure.co.uk
How we can help | Sovereign Secure Ltd is a PCI SSC Qualified Security Assessor (QSA) company, an IASME-licensed Cyber Essentials certification body and ISO 27001 certified. We deliver network, application, cloud and social engineering penetration testing and will work through this checklist with you during scoping.
Sovereign Secure Ltd (Sovereign Secure Limited), company number 08334453. 16 Whalley Road, Accrington, Lancashire, BB5 1AA. sovereignsecure.co.uk

## Checklist
Penetration test preparation checklist
Free template from Sovereign Secure Ltd ¦ sovereignsecure.co.uk ¦ +44 161 523 5276 ¦ Version October 2026 ¦ Before, during and after the test
What your team needs to do before, during and after a penetration test, in the order it usually happens. Adjust the timings to your test: complex or multi-site tests need longer. Add the person responsible and a target date for each task.
ID | When | Task | Usual owner | Person responsible | Target date | Status | Notes
P-01 | 4 weeks before | Agree why you are testing (compliance, customer or insurer assurance, change, checking earlier fixes) and write it down | Executive sponsor, IT lead
P-02 | 4 weeks before | Gather scoping details: external IPs, domains and hostnames; internal sites, subnets, hosts and users; web apps and APIs with user roles; cloud accounts; wireless, physical sites or people if relevant | IT lead
P-03 | 4 weeks before | Note any compliance requirement the test must meet (for example PCI DSS 11.4) and your deadline | IT lead
P-04 | 4 weeks before | Decide how much information testers get: black box, grey box or white box | IT lead
P-05 | 4 weeks before | Confirm scope and exclusions in writing (fragile systems, third-party services you do not own, production data) | IT lead
P-06 | 3 weeks before | Sign the rules of engagement and written authorisation | IT lead, legal
P-07 | 3 weeks before | Agree testing dates and windows, blackout periods, techniques not permitted and limits on password guessing | IT lead
P-08 | 3 weeks before | Name emergency contacts on both sides and agree how to stop testing immediately | IT lead
P-09 | 2 weeks before | Check your cloud providers' published testing rules | IT lead
P-10 | 2 weeks before | Notify hosting providers where contracts require it | IT lead
P-11 | 2 weeks before | Brief managed security or SOC providers, unless you are deliberately testing their detection | IT lead
P-12 | 2 weeks before | Brief IT and operations on the testing window and what to expect | IT lead
P-13 | 2 weeks before | Involve HR and legal if phishing, phone pretexting or physical access is in scope | IT lead, HR, legal
P-14 | 1 week before | Create test accounts for each role in scope (two per role for applications) and set up MFA tokens for testers | System owners
P-15 | 1 week before | Allow-list tester IP addresses where agreed | System owners
P-16 | 1 week before | Take backups of in-scope systems and confirm you can restore them | System owners
P-17 | 1 week before | Share documentation: network diagrams, API specifications and user guides | System owners
P-18 | 1 week before | Stabilise the environment (nothing mid-deployment, realistic test data) and check logging and monitoring | System owners
P-19 | Day one | Named contact available; remote appliance connected if used | IT lead
P-20 | During the test | Keep one named contact available and avoid major changes to in-scope systems | IT lead
P-21 | During the test | If you fix a reported critical issue mid-test, tell the testers | IT lead
P-22 | After the report | Hold a debrief with the testers and the teams who will fix the issues | Executive sponsor
P-23 | After the report | Assign an owner and target date to every finding | Executive sponsor
P-24 | After the report | Book a retest of the fixed issues | Executive sponsor